**Saturday – 9/23**

10:00am Start

* Set Up Zone 1…Bays SU1, SU2, SU3…Stages 1, 2, 3
* Move plate rack from south conex to SU2
* Distribute as much material *(that won’t be misused)* as possible to outside of all other bays/stages

**Sunday – 9/24**

10:00am Start

* Set Up Zone 1…Bays SU4, SU5, SU6…Stages 4, 5, 6
* Move plate rack from holding area to SU5
* Remove flakey plate rack from SU5
* Identify locations & setup 6x Safety Area tables & fault lines
* Place signs at 5x established railroad tie Safety Areas

**Monday – 9/25**

10:00am Start

* Set Up Zone 2…Bays R1🡪Inst7…Stages 7🡪12 + Function Bay

**Tuesday – 9/26**

10:00am Start

* Set Up Zone 2…Bays R1🡪Inst7…Stages 7🡪12 + Function Bay

**Wednesday – 9/27**

10:00am Start

* Distribute pre-packed blank & hardcover cardboard target bags to each bay
* Staple cardboard targets in all bays
* If Weds thru Sunday weather forecast dictates (Patrice??)…distribute rain bags to each bay

12:00pm

* Dan & Germaine walk through, bless all stages, and calibrate all steel.

*(accompanied by staff to make necessary tweaks)*

* Witness mark all targets, prop positions, swinger weights, etc.
* Ensure all pre-packed blank & hardcover cardboard target bags are secured & protected
* Mounted carboard targets are left in place *(weather permitting)*

**Thursday – 9/28**

7:00am

* Pre-match staff meeting (all assigned CRO/RO’s shooting on Thursday) at Rifle 1 Bay

8:00am

* Staff squads 101-103, squad 151 shoot all 12 stages

12:10pm – Lunch

5:00pm

* Last shots
* Mounted carboard targets are left in place *(weather permitting)*

**Friday – 9/29**

8:00am

* Staff squads 104-106 & squad 201 shoot all 12 stages

12:10pm -- Lunch

5:00pm

* Last shots
* Mounted carboard targets are left in place *(weather permitting)*

**Saturday – 9/30**

7:00am

* Main match staff meeting at the Archery Range.

8:00am

* 1st shoots - main match schedule

10:00am

* Quartermaster distributes 2 sets of blank cardboard targets for afternoon schedule

12:30pm – Lunch

5:00pm

* Last shots
* Mounted carboard targets are left in place *(weather permitting)*

**Sunday – 10/1**

6:30am

* Quartermaster distributes 2 sets of blank cardboard targets for morning schedule

8:00am

* 1st shoots - main match schedule

12:30pm

* Last shots
* Lunch
* Arbitration Period

1:30pm – (following arbitration Period)

* Squads break down stages
* PPGC stored material moved to respective PPGC storage locations
* CRC (Orange), Regis (Red), and Germaine (Yellow) material left at ends of bays or moved to holding area

2:30pm – Awards ceremony at the PPGC lodge

**Monday – 10/2**

10:00am Start

* All Regis & Germaine material transported back to Regis range

**Tuesday – 10/3**

10:00am Start

* All CRC material transported back to CRC